## Gantt Chart w % Complete
Build better gantt charts with TeamGantt for FREE!
* = an automatically calculated cell
| TASK NAME | START DATE | DAY OF MONTH* | END DATE | DURATION* (WORK DAYS) | DAYS COMPLETE* | DAYS REMAINING* | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 5 | 2018-01-08 | 4 | 4 | 0 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 8 | 2018-01-11 | 4 | 3.2 | 0.8 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 11 | 2018-01-16 | 6 | 3.6 | 2.4 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 14 | 2018-01-19 | 6 | 2.4 | 3.6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 17 | 2018-01-23 | 7 | 1.4 | 5.6 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 9 | 2018-01-12 | 4 | 4 | 0 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 12 | 2018-01-19 | 8 | 6.4 | 1.6 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 17 | 2018-01-19 | 3 | 1.8 | 1.2 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 22 | 2018-01-26 | 5 | 2 | 3 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 15 | 2018-01-19 | 5 | 5 | 0 | Nathan | 100%
| Reserve Room | 2018-01-22 | 22 | 2018-01-23 | 2 | 1.6 | 0.4 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 22 | 2018-01-26 | 5 | 3 | 2 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 26 | 2018-01-29 | 4 | 1.6 | 2.4 | Michael | 40%
| Create Invitations | 2018-01-22 | 22 | 2018-01-25 | 4 | 0.8 | 3.2 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 15 | 2018-01-24 | 10 | 10 | 0 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 25 | 2018-01-30 | 6 | 4.8 | 1.2 | Meredith | 80%
| Update Messaging | 2018-01-24 | 24 | 2018-01-30 | 7 | 4.2 | 2.8 | Michael | 60%
| Publish Calculator | 2018-01-30 | 30 | 2018-01-31 | 2 | 0 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Basic Gantt Chart
GANTT CHART TEMPLATE
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
First Sample Project
| Write Landing Page Copy | 2018-01-05 | 2018-01-08 | 0 | 4 | Nathan | 100%
| Approve Page Copy | 2018-01-08 | 2018-01-11 | 3 | 4 | Meredith | 80%
| Review Landing Page Design | 2018-01-11 | 2018-01-16 | 6 | 6 | Brandon | 60%
| Build Landing Page | 2018-01-14 | 2018-01-19 | 9 | 6 | Michael | 40%
| Code Review Landing Page | 2018-01-17 | 2018-01-23 | 12 | 7 | Rachel | 20%
Second Sample Project
| Write Promotional Email | 2018-01-09 | 2018-01-12 | 4 | 4 | Nathan | 100%
| Design Promotional Email | 2018-01-12 | 2018-01-19 | 7 | 8 | Meredith | 80%
| Send Promotional Email | 2018-01-17 | 2018-01-19 | 12 | 3 | Brandon | 60%
| Analyze Campaign Results | 2018-01-22 | 2018-01-26 | 17 | 5 | Michael | 40%
Third Sample Project
| Plan Agenda for Meeting | 2018-01-15 | 2018-01-19 | 10 | 5 | Nathan | 100%
| Reserve Room | 2018-01-22 | 2018-01-23 | 17 | 2 | Meredith | 80%
| Finalize Presentation | 2018-01-22 | 2018-01-26 | 17 | 5 | Brandon | 60%
| Approve Presentation | 2018-01-26 | 2018-01-29 | 21 | 4 | Michael | 40%
| Create Invitations | 2018-01-22 | 2018-01-25 | 17 | 4 | Rachel | 20%
Fourth Sample Project
| Rewrite Online Calculator | 2018-01-15 | 2018-01-24 | 10 | 10 | Nathan | 100%
| Code Review Calculator | 2018-01-25 | 2018-01-30 | 20 | 6 | Meredith | 80%
| Update Messaging | 2018-01-24 | 2018-01-30 | 19 | 7 | Michael | 60%
| Publish Calculator | 2018-01-30 | 2018-01-31 | 25 | 2 | Rachel | 0%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Manual Chart
GANTT CHART TEMPLATE
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10
[7 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Initial Research
| Note reading | 2022-02-21 | 2022-03-11 | 15 | ALL | 100% | bar: WEEK 2 Mon to WEEK 2 Tue
| learn and understand the whole program | 2022-03-11 | 2022-03-15 | 3 | ALL | 100% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 6 Mon to WEEK 6 Tue
| Group division | 2022-03-11 | 2022-03-15 | 3 | ALL | 100% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 6 Mon to WEEK 6 Tue
Data processor
| Identify the general idea | 2022-02-28 | 2022-03-03 | 4 | Yanbo & Fan | 100% | bar: WEEK 2 Mon to WEEK 2 Tue
| Design the FSM chart | 2022-03-03 | 2022-03-07 | 3 | Yanbo & Fan | 100% | bar: WEEK 2 Mon to WEEK 2 Tue
| Labor Division | 2022-03-07 | 2022-03-08 | 2 | Yanbo & Fan | 80% | bar: WEEK 2 Mon to WEEK 2 Tue
| State machine(Mealy machine) | 2018-02-11 | 2018-02-16 | 5 | Fan | 60% | bar: WEEK 2 Mon to WEEK 2 Tue
| Comparison and Calculation | 2018-02-08 | 2018-02-13 | 4 | Yanbo & Fan | 80% | bar: WEEK 2 Mon to WEEK 2 Tue
| Debug and Board application | 2018-02-11 | 2018-02-16 | 5 | Yanbo & Fan | 60% | bar: WEEK 2 Mon to WEEK 2 Tue
| Write the data's report | 2018-02-11 | 2018-02-16 | 5 | Fan | 60% | bar: WEEK 2 Mon to WEEK 2 Tue
Command processor
| Identify the general idea | 2022-02-28 | 2022-03-01 | 2 | Xinyi & Jingrong & kaichen | 100% | bar: WEEK 1 Mon to WEEK 1 Tue; WEEK 2 Mon to WEEK 2 Tue
| Design the FSM chart | 2022-03-01 | 2022-03-05 | 4 | Xinyi & Jingrong | 100% | bar: WEEK 1 Tue to WEEK 1 Sat; WEEK 2 Mon to WEEK 2 Tue
| Labor Division | 2022-03-05 | 2022-03-07 | 1 | Xinyi & Jingrong | 100% | bar: WEEK 1 Sat to WEEK 2 Tue
| State machine(Mealy machine) | 2022-03-07 | 2022-03-25 | 15 | Xinyi | 100% | bar: WEEK 2 Mon to WEEK 4 Fri
| Rx Design | 2022-03-07 | 2022-03-25 | 15 | Jingrong | 100% | bar: WEEK 2 Mon to WEEK 4 Fri
| Tx Design | 2022-03-10 | 2022-03-25 | 12 | Kaichen | 100% | bar: WEEK 2 Thu to WEEK 4 Fri
| Debug and Board application | 2022-03-26 | 2022-04-09 | 10 | Xinyi & Jingrong & kaichen | 100% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 4 Sat to WEEK 6 Sat
| Write the data's report | 2022-04-10 | 2022-04-25 | 11 | Xinyi & Jingrong & kaichen | 100% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 6 Sun to WEEK 9 Mon
Deadlines
| Connet the data and command | 2022-04-10 | 2022-04-12 | 2 | Yanbo & Xinyi | 100% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 6 Sun to WEEK 7 Tue
| Global debug | 2022-04-10 | 2022-04-12 | 2 | Yanbo &Xinyi | 80% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 6 Sun to WEEK 7 Tue
| Organize the two reports | 2022-04-20 | 2022-04-23 | 3 | ALL | 60% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 8 Wed to WEEK 8 Sat
| Rflection | 2022-04-24 | 2022-04-25 | 1 | ALL | 40% | bar: WEEK 2 Mon to WEEK 2 Tue; WEEK 8 Sun to WEEK 9 Mon
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])